## 프로젝트 플래너
프로젝트 플래너
오른쪽에서 강조 표시할 기간을 선택합니다. 그 다음, 차트를 설명하는 범례가 나옵니다. |  |  |  |  | 기간 강조 표시: | 1 |  |  | 기간 계획 |  |  |  | 실제 시작 |  |  |  | % 완료 |  |  | 실제(계획을 넘어서는) | [6 empty] | % 완료(계획 초과)
활동 | 계획 시작 | 기간 계획 | 실제 시작 | 실제 기간 | 완료율 | 기간
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
First | 1 | 1 | 1 | 1 | 100%
Login Page | 1 | 5 | 7 | 0 | 20%
Home_Logo | 1 | 1 | 1 | 1 | 100%
Home_Nav bar | 1 | 1 | 1 | 1 | 100%
Home_Size | 1 | 1 | 1 | 1 | 100%
Home_NewReview(Img) | 1 | 1 | 1 | 1 | 100%
Home_BestReview(Img) | 1 | 1 | 1 | 1 | 100%
Home_Have | 3 | 1 | 3 | 1 | 100%
Home_Popular | 3 | 1 | 3 | 1 | 100%
Home_Popular(ShoeImg) | 3 | 1 | 3 | 1 | 100%
Home_Popular(ShoeId) | 3 | 1 | 3 | 1 | 100%
Home_Popular(ShoeName) | 3 | 1 | 3 | 1 | 100%
Home_Popular(ShoeScore) | 3 | 1 | 3 | 1 | 100%
Product_Menu(Brands) | 4 | 1 | 0 | 1 | 100%
Product_Menu(ShoeImg) | 4 | 1 | 0 | 5 | 100%
Product_Menu(ShoeId) | 4 | 1 | 0 | 3 | 100%
Product_Menu(ShoeName) | 4 | 1 | 0 | 5 | 100%
Product_Menu(ShoeScore) | 4 | 1 | 0 | 7 | 100%
Review_Main | 5 | 1 | 0 | 5 | 100%
Review_Main(ShoeImg) | 5 | 1 | 0 | 6 | 100%
Review_Main(ShoeName) | 5 | 1 | 0 | 2 | 100%
Review_Main(ShoeId) | 5 | 1 | 0 | 3 | 100%
Review_Main(ShoeScore) | 5 | 1 | 0 | 8 | 100%
Review_Main_AI | 6 | 1 | 0 | 3 | 100%
Review_Main_Summ1 | 6 | 1 | 0 | 5 | 100%
Review_Main_Summ2 | 6 | 1 | 0 | 30 | 100%
Review_Main_Summ3 | 6 | 1 | 0 | 50 | 100%
Review_All | 7 | 1 | 0 | 50 | 100%
Review_Filter | 7 | 1 | 0 | 50 | 0%
Review_Filter(Size) | 7 | 1 | 0 | 50 | 0%
Review_Filter(Width) | 7 | 1 | 0 | 50 | 0%
Review_Filter(Height) | 7 | 1 | 0 | 50 | 0%
Review_Filter(Adapt) | 7 | 1 | 0 | 50 | 0%
Review_User | 7 | 1 | 0 | 50 | 0%
Review_User(Have) | 7 | 1 | 0 | 50 | 0%
Review_User(Review) | 7 | 1 | 0 | 50 | 0%
MyPage_Main | 8 | 1 | 0 | 50 | 0%
MyPage_Have | 8 | 1 | 0 | 50 | 0%
MyPage_Have_Add | 8 | 1 | 0 | 50 | 0%
MyPage_Have_Review | 8 | 1 | 0 | 50 | 0%
MyPage_Reviews | 8 | 1 | 0 | 50 | 0%
MyPage_Reviews_reviews | 8 | 1 | 0 | 50 | 0%
MyPage_Reviews_Update | 8 | 1 | 0 | 50 | 0%
MyPage_Reviews_Delete | 8 | 1 | 0 | 50 | 0%
MyPage_Size | 9 | 1 | 0 | 50 | 0%
Mypage_Profile | 9 | 1 | 0 | 50 | 0%
Mypage_Profile_Add | 9 | 1 | 0 | 50 | 0%
Mypage_Profile_Update | 9 | 1 | 0 | 50 | 0%
Mypage_Profile_Delete | 9 | 1 | 0 | 50 | 0%
Profile_Menu | 10 | 1 | 0 | 50 | 0%
Profile_Logout | 10 | 1 | 0 | 50 | 0%
Admin_Add | 10 | 1 | 0 | 50 | 0%
Admin_Add(ShoeImg) | 10 | 1 | 0 | 50 | 0%
Admin_Add(ShoeName) | 10 | 1 | 0 | 50 | 0%
Admin_Add(ShoeBrand) | 10 | 1 | 0 | 50 | 0%
Admin_Add(ShoeId) | 10 | 1 | 0 | 50 | 0%
Admin_Manage | 11 | 1 | 0 | 50 | 0%
Admin_Manage_Add | 11 | 1 | 0 | 50 | 0%
Admin_Manage_Update | 11 | 1 | 0 | 50 | 0%
Admin_Manage_Delete | 11 | 1 | 0 | 50 | 0%